PENNYPILOT AI

AI Shopping & Money Recovery Agent

Hackathon implementation blueprint

A shared, build-ready plan for a two-person team working to a 10-day delivery window and a ₹0 preferred budget.

CORE PROMISE Find the right product at the right price, stay in control of shopping spend, and know what was spent, what should be refunded, what remains unresolved, and what action to take next.

Prepared: 24 October 2026

Team setup: 2 people • Intermediate technical level • 10 days • Prefer free tools

Document status: Implementation plan; API access, pricing-source availability, and hosting terms must be verified during setup.

# How to use this document

Use this as the team's shared source of truth. Build in the order specified, keep scope tight, and do not mark a capability complete until its acceptance test passes.

Person A owns payment integration, backend, data model and webhook reliability.

Person B owns AI workflows, pricing data, Streamlit UI and user experience.

Both team members review integration contracts, test the end-to-end workflow, document setup, and rehearse the demo.

Keep one GitHub issue per deliverable and merge small pull requests frequently.

SCOPE RULE A functional, honest prototype is stronger than a broad product full of mocked integrations. Clearly label sample price data and user-entered external purchases.

# 1. Executive summary

PennyPilot AI is a shopping assistant that connects pre-purchase decisions with post-purchase accountability. It compares supported product offers, tracks price history and target prices, helps users reason about shopping budgets, and records purchases, returns and refunds at item level. Its AI interprets receipts and return evidence, explains discrepancies, and proposes next actions. PayPal Sandbox demonstrates a real test payment/refund lifecycle and event-driven status updates.

The product is not positioned as a universal connection to every retailer or bank. PayPal APIs and webhooks cover events associated with the app/integration and eligible PayPal transactions; unrelated purchases require user-provided evidence or a separately authorized source.

| Goal | MVP proof |
| --- | --- |
| Meaningful PayPal use | Sandbox order approval/capture, eligible partial refund, stored capture/refund IDs, webhook-driven update. |
| Meaningful AI use | Receipt field extraction plus evidence-grounded refund discrepancy explanation. |
| Shopping assistance | Product comparison/watchlist from a documented data source or clearly labelled sample dataset; price-history chart and target-price alert. |
| Financial correctness | Item-level return and refund accounting; outstanding balance calculated by code; duplicate event protection. |
| Submission readiness | Working demo, public source repo, license, complete README, tools disclosure, and public YouTube video under 3 minutes. |

# 2. Market problem

## 2.1 User pain points

Price fragmentation: the same product can have different prices, delivery charges, seller conditions and availability across retailers.

Timing uncertainty: consumers see a price today but may not know whether it is unusually high relative to recent history.

Budget fragmentation: planned purchases, actual spending and pending refunds are often tracked separately.

Refund visibility: returns and refunds can occur at different times; partial returns can create partial or multiple refunds.

Manual reconciliation: users may need to compare order pages, return confirmations, emails and payment statements to understand what is still outstanding.

Unstructured evidence: receipts and return messages contain useful fields but are not always stored in a consistent format.

## 2.2 Proposed user value

| Before purchase | During/after purchase | When something goes wrong |
| --- | --- | --- |
| Compare supported offers; inspect history; set target price; consider budget. | Record order, items and payment reference; store receipt; track return status. | Calculate expected vs confirmed refund; flag discrepancy; prepare a follow-up for user review. |

## 2.3 What success means

The user can explain the status and outstanding amount of a partial refund without manually calculating it.

A supported PayPal sandbox event changes the app's stored state after verification.

The user can inspect product price history and create a target-price alert.

AI outputs are traceable to records and uncertainty is explicit.

# 3. Product definition and differentiation

## 3.1 Product statement

PennyPilot AI is an AI shopping and money recovery agent that helps consumers find better prices, manage planned purchases, reconcile returns against confirmed refunds, and take evidence-backed next steps.

## 3.2 Core modules

| Module | MVP functionality | Not promised in MVP |
| --- | --- | --- |
| Shopping Intelligence | Compare offers from one supported source or labelled sample data; history chart; target price; price-drop alert. | Universal real-time coverage across all retailers; guaranteed prediction. |
| Shopping Budget | Wishlist, planned spend, recorded purchases and simple monthly totals. | Full bank aggregation or automated access to every account. |
| Refund Guardian | Order-level and item-level records; expected/received/outstanding totals; partial refunds; statuses. | Automatic access to unrelated retailer accounts. |
| AI Receipt Assistant | Extract merchant, date, item, amount and reference from uploaded evidence; user can correct fields. | Treating OCR/LLM output as verified financial truth. |
| Action Assistant | Explain discrepancy; prioritize follow-up; draft a support message for review. | Sending messages or issuing financial actions without user approval. |

## 3.3 Differentiation

Closed-loop workflow: detect → reconcile → recommend → user approves action → track outcome.

Item-level accounting: one order may contain several products, each with its own return and refund lifecycle.

Evidence timeline: link order, return evidence, payment capture, refund event, discrepancy and resolution.

Trustworthy AI: AI extracts and explains; deterministic code calculates money and validated payment events control verified status.

Combined shopping context: price decisions and unresolved refunds are shown in the same assistant, without claiming that an outstanding refund is spendable cash.

# 4. Hackathon requirement mapping

| Hackathon requirement | PennyPilot implementation | Evidence to show judges |
| --- | --- | --- |
| Meaningful PayPal technology | PayPal REST APIs in Sandbox for order creation/capture and eligible capture refund; webhook listener for subscribed events. | Live sandbox flow; IDs/status in app; event log; code path and README. |
| Meaningful AI | LLM structured receipt extraction and record-grounded discrepancy explanations/action suggestions. | Upload sample receipt; inspect extracted JSON; ask why refund is outstanding. |
| Working prototype | Interactive Streamlit UI connected to database and API/service functions. | Hosted demo or reproducible local run instructions. |
| Documentation | README, architecture, environment setup, known limitations, test instructions and tool disclosure. | Public repository with complete setup steps. |
| Public open-source repository | GitHub public repository with license file at repository root. | Repository URL and visible LICENSE. |
| Demo video under 3 minutes | Show a functioning workflow on the target device; no unlicensed music/assets. | Public YouTube URL in submission. |
| Sponsor tools optional | Postman and Render may be used; no sponsor tool is required. | Document actual tools used and purpose. |

JUDGING STRATEGY Do not treat a PayPal logo, a static mock-up, a fake webhook, or an AI-only chatbot as sufficient integration. Demonstrate the API-backed lifecycle and explain exactly what the sandbox does and does not prove.

# 5. Technology stack and cost plan

## 5.1 Recommended ₹0-first stack

| Layer | Tool | Use | Cost position / caveat |
| --- | --- | --- | --- |
| UI | Streamlit | Dashboard, forms, tables, charts and AI interaction. | Open-source; hosted free options have quotas and operational limits. |
| Application logic | Python 3.11+ (or supported current version) | Refund calculations, validation, integration services. | Free/open-source. |
| Payment | PayPal REST APIs — Sandbox | Create order, capture payment, refund eligible capture. | Sandbox testing is intended for test transactions; live payment fees are not part of this MVP. |
| Events | PayPal Webhooks | Receive subscribed events and update the ledger. | Part of PayPal API workflow; endpoint must be reachable over HTTPS for deployed delivery. |
| AI | Local model via Ollama OR an LLM API | Receipt extraction, explanations, action drafts. | Local model can avoid per-call API charges but needs suitable hardware; hosted APIs are generally usage-billed unless current credits/promotions apply. |
| Database | SQLite locally; PostgreSQL if hosted multi-user persistence is required | Orders, items, returns, refunds, events, products, prices and alerts. | SQLite is free; managed database free tiers have limits and expiry/retention terms to verify. |
| Data processing | Pandas, NumPy | Price history, aggregation and basic analysis. | Free/open-source. |
| Charts | Plotly | Price history and dashboard visualizations. | Free open-source library. |
| Price source | Documented API if suitable; otherwise labelled sample CSV | Offers and timestamped price observations. | Provider access, coverage and historical data can be paid or restricted. Do not assume free access. |
| Scheduling | APScheduler or host-supported scheduled jobs | Target-price and overdue-case checks. | Library is free; hosting/background execution limits may apply. |
| Testing | Pytest and Postman | Unit tests, API requests and debugging. | Free options available; product tiers/quotas vary. |
| Source control | Git + GitHub | Public repo, issues, pull requests, README and license. | Core free features are sufficient for this MVP. |
| Deployment | Render or another compatible host | Host web app/API for judge access. | Free tier available with restrictions; sleeping, storage, bandwidth and job limitations must be considered. |

## 5.2 Paid options (not required for first build)

| Potential paid component | Why consider it | Decision rule |
| --- | --- | --- |
| Hosted LLM API | Better quality or simpler deployment than a local model. | Use only if free/local model quality is insufficient; set a small usage budget and avoid sending unnecessary personal data. |
| Commercial product/price API | Structured offers, retailer coverage or price history unavailable from free sources. | Validate retailer coverage, price-history access, terms, quotas and price before integration. |
| Paid hosting/database | Always-on service, persistent storage, background jobs or stable demo availability. | Upgrade only if free hosting blocks a required feature; otherwise use local demo instructions as fallback. |
| Email/SMS notification provider | External alerts beyond in-app notifications. | Not essential to MVP; use in-app alerts first. |

₹0 BUDGET CONTROL A zero-cost prototype is feasible if the team uses PayPal Sandbox, open-source Python libraries, local SQLite, sample price data and a local model or currently available free AI allowance. Do not assume that an LLM API or live product-price API is free. Confirm current pricing and quotas before selecting a provider.

## 5.3 Official references to verify during setup

PayPal REST API overview: https://developer.paypal.com/api/rest/

PayPal getting started and Sandbox accounts: https://developer.paypal.com/api/get-started/

PayPal REST webhooks integration: https://developer.paypal.com/api/rest/webhooks/rest/

PayPal webhooks overview: https://developer.paypal.com/api/webhooks/overview/

Render free deployment limits: https://render.com/docs/free

Render pricing: https://render.com/pricing

# 6. System architecture

Recommended MVP: Streamlit frontend, Python service modules, SQLite in local development, a PayPal API client, an HTTPS webhook endpoint, an AI adapter, and a price-data adapter. If Streamlit hosting cannot expose a reliable webhook endpoint, run a small FastAPI service separately or use a public HTTPS deployment. Keep business logic independent of the UI.

| Component | Responsibility | Boundary |
| --- | --- | --- |
| Streamlit UI | User interaction, tables, forms, charts, upload and status display. | Does not decide whether payment/refund is verified. |
| Python service layer | Order/item/refund rules, validation, matching and status transitions. | Financial arithmetic is deterministic. |
| PayPal client | OAuth token, order creation, capture, refund and resource lookup where supported. | Use server-side secret; only operate on transactions the integration is authorized to access. |
| Webhook endpoint | Receive events, verify signature, deduplicate, persist event and update state. | Only verified events can update verified payment status. |
| AI adapter | Extract structured data and produce explanations based on selected records. | AI output is untrusted until validated/user-confirmed. |
| Price adapter | Read supported API or sample data and normalize offers. | Record source and timestamp; label sample data. |
| Database | Persist orders, items, returns, refunds, webhook events, prices and alerts. | Avoid storing unnecessary personal/financial information. |
| Scheduler | Evaluate target-price and overdue-refund rules on a schedule. | Do not promise continuous monitoring on a host that sleeps or blocks background jobs. |

## 6.1 Main data flow

User adds a planned purchase or records/uploads an external order receipt.

AI extracts candidate fields and returns structured output with confidence/uncertainty; user reviews uncertain fields.

Validated order and item records are stored in the database.

For the PayPal demo, backend creates a sandbox order, buyer approves it, and backend captures it.

App stores PayPal order ID and capture ID with currency and amount.

User/test flow initiates a permitted partial or full refund against the eligible capture.

PayPal sends a subscribed webhook event to the public HTTPS endpoint; backend verifies the event and records it idempotently.

Refund service recalculates confirmed amount and outstanding balance; UI reflects the new state.

Price adapter stores timestamped observations; scheduler checks target-price thresholds and creates in-app alerts.

AI assistant reads only the relevant records and explains the current state, citing the data it used in the UI.

# 7. Database design

Use relational tables with primary keys and explicit relationships. Store monetary values as integer minor units when practical, plus ISO currency code; otherwise use decimal arithmetic. Do not use binary floating-point for money.

| Table | Important fields | Purpose / notes |
| --- | --- | --- |
| orders | order_id PK, merchant, order_date, currency, original_amount_minor, source_type, paypal_order_id nullable, capture_id nullable | One row per order. source_type distinguishes PayPal Sandbox from user-entered/receipt-based orders. |
| order_items | item_id PK, order_id FK, product_name, quantity, unit_price_minor, discount_minor, refundable_amount_minor | One row per item/SKU line; store agreed refundable amount only when supported. |
| returns | return_id PK, item_id FK, quantity_returned, requested_at, status, evidence_ref | Return lifecycle per item/quantity; do not assume request means approval. |
| refunds | refund_id PK, order_id FK, item_id nullable FK, provider_refund_id nullable, expected_amount_minor, confirmed_amount_minor, currency, status, expected_by, confirmed_at | One row per refund expectation/event. Some provider refunds may only map to the order, not an item. |
| payment_events | event_id PK, provider_event_id UNIQUE, event_type, resource_id, received_at, verified, processing_status, payload_hash | Deduplication and audit trail. Store minimum payload needed; avoid logging secrets. |
| products | product_id PK, canonical_name, brand/model, category, external_identifier nullable | Catalog identity for comparisons. |
| price_history | price_observation_id PK, product_id FK, retailer, observed_at, amount_minor, currency, availability, source, is_sample | Every price must carry source/time; sample data must be labelled. |
| alerts | alert_id PK, alert_type, related_record_id, created_at, message, status, threshold_minor nullable | In-app price/refund alerts. |
| ai_extractions | extraction_id PK, source_ref, extracted_json, confidence/field flags, user_confirmed, created_at | Optional audit of extraction corrections; do not store raw documents longer than needed. |

## 7.1 Core calculation

Outstanding refund = max(0, total expected refund − total confirmed refund amount).

Expected refund must be based on returned items and any known adjustments, not on the full original order amount. Keep expected and confirmed amounts separate. If actual provider data does not identify the item, do not invent an allocation; flag it as order-level/unmatched for review.

## 7.2 Example test case

| Item | Price | Returned? | Expected refund | Confirmed refund |
| --- | --- | --- | --- | --- |
| Shirt | ₹2,000 | Yes | ₹2,000 | ₹2,000 |
| Shoes | ₹1,800 | Yes | ₹1,800 | ₹0 |
| Watch | ₹1,200 | No | ₹0 | ₹0 |
| Total | ₹5,000 | — | ₹3,800 | ₹2,000 |

Expected outstanding amount: ₹3,800 − ₹2,000 = ₹1,800, assuming the full listed item amounts are refundable and no fees/discount adjustments apply.

# 8. PayPal integration: precise implementation flow

## 8.1 What is supported vs what is not assumed

| Capability | Plan / limitation |
| --- | --- |
| Sandbox checkout/order | Use PayPal Orders API to create the order; buyer approval; server-side capture. Follow current PayPal Checkout docs. |
| Refund of a captured payment | Use the supported Payments/Captures refund operation for an eligible capture; store returned refund ID/status. |
| Webhook event delivery | Subscribe the app to relevant events and expose a reachable HTTPS listener. Verify the message before changing verified status. |
| Transactions from unrelated merchant integrations | Do not assume access. Events are associated with the app/integration and transactions processed in its context. |
| Myntra/other retailer returns | Need retailer-authorized API/data, an authorized financial data source, or user-uploaded/manual evidence. PayPal Sandbox does not create access to third-party retailer accounts. |
| Refund success semantics | Use the provider's returned resource/status and later event/resource lookup as appropriate; do not infer success from an AI model or a return request. |

## 8.2 PayPal implementation sequence

Create PayPal Developer account and a REST app in Sandbox; create/test buyer and merchant sandbox accounts.

Keep client secret in environment variables; obtain OAuth 2.0 access token server-side.

Implement create-order endpoint/service and return approval URL or use the approved checkout integration pattern.

Capture the approved order server-side and persist order ID, capture ID, amount, currency and response status.

Implement a refund action against the eligible captured payment; support a specific amount for partial-refund tests where allowed.

Register webhook event types needed for capture/refund lifecycle and store the webhook ID for verification.

Implement an HTTPS webhook endpoint. Verify signature using PayPal's documented mechanism before processing.

Persist provider event ID with a unique constraint; if already processed, acknowledge safely without applying the refund twice.

Update payment/refund records and recompute the outstanding amount. Keep an audit trail for each transition.

Test duplicate, out-of-order, invalid-signature, retry and failed-event cases.

REGIONAL ACCESS CHECK PayPal's current getting-started guidance notes account requirements for going live and testing outside the US. During Day 1, confirm that the team can create/use the required Sandbox app and accounts from its region; do not postpone this discovery.

# 9. AI implementation design

## 9.1 AI tasks

| Task | Input | Output | Safety/validation |
| --- | --- | --- | --- |
| Receipt extraction | Image/PDF/text receipt | Merchant, date, order ID, item rows, quantities, prices, currency | Validate schema and totals; mark low-confidence fields; user confirms. |
| Return evidence extraction | Return confirmation/email text | Item, return reference, status language, expected refund if present | Do not treat text as provider-confirmed refund. |
| Discrepancy explanation | Order/item/refund records and verified events | Plain-language explanation and evidence used | Numbers come from code/database, not generated by model. |
| Next-action suggestion | Overdue/discrepancy rules and available evidence | Suggested action and draft message | User reviews; no automatic message sending in MVP. |
| Shopping recommendation | Price history, target, budget, data quality | Buy/wait/insufficient evidence with explanation | No guaranteed price predictions; show sample vs live data. |

## 9.2 Suggested tool-calling functions

get_order(order_id)

get_order_items(order_id)

get_refund_status(order_id)

get_outstanding_refunds()

get_product_price_history(product_id)

create_price_alert(product_id, target_price)

Start with read-only tools and allow only validated, explicit actions such as creating an alert. Payment/refund actions must be protected by server-side rules and user confirmation. Never give the model unrestricted database or shell access.

## 9.3 AI provider choice

₹0-first option: run a suitable local model through Ollama if the team's computer has enough memory/compute. Quality, speed and image support vary; test early.

Convenience option: hosted LLM API. This is generally paid by usage unless the account currently has eligible credits or a free allowance. Set a budget cap and never place API keys in the browser or repository.

Use structured JSON output and validate it with Pydantic or equivalent. Keep sample receipts synthetic or redacted.

# 10. Price comparison and forecast design

## 10.1 Data-source plan

A price comparison feature needs a legitimate source of product offers and, for trend analysis, timestamped historical observations. Do not assume retailer websites permit scraping or offer public APIs.

Preferred: a product/price API whose terms explicitly permit the planned use and which covers the target retailers.

Fallback for hackathon: a small, clearly labelled sample CSV containing product, retailer, timestamp, price, currency, availability and source fields.

Never display sample prices as live data. Include a visible 'Sample data' label and source/time on each observation.

## 10.2 Minimum viable price functions

Normalize product identity, currency, shipping and seller conditions where available.

Show current offers and the last observed time.

Plot price history and calculate recent minimum/maximum/average.

Allow target-price setting and trigger an in-app alert when a new observation crosses the threshold.

Forecast only when enough observations exist; compare with a simple baseline and display uncertainty. Otherwise show 'not enough data'.

## 10.3 Budget-aware assistant

Use a simple budget rule for the MVP: planned purchase amount, user-set monthly budget, recorded spending and outstanding refunds displayed separately. Do not count pending refunds as money already available. Recommendations should be advisory, transparent and non-coercive.

# 11. Ten-day implementation plan

Assumption: two people can contribute roughly 6–8 focused hours each per day. The plan has limited contingency; protect the final two days for integration, documentation and submission.

| Day | Person A — backend/PayPal/data | Person B — AI/UI/pricing | Dependency / exit criterion |
| --- | --- | --- | --- |
| 1 | Create repo, environment, PayPal app and sandbox accounts; test OAuth/API access. | Create Streamlit shell, user flow sketch, sample receipt and sample price dataset. | PayPal Sandbox access proven; app launches locally; scope frozen. |
| 2 | Design schema and implement database/repository functions. | Build dashboard skeleton and item/order/return forms using service interfaces. | Schema agreed; sample order can be stored and read. |
| 3 | Implement order creation, approval/capture and persistence of IDs. | Implement receipt upload, structured extraction adapter and manual correction UI. | Sandbox capture works; extracted fields can be reviewed/saved. |
| 4 | Implement refund request against eligible capture and persist returned status/ID. | Implement item-level return UI and expected/confirmed/outstanding views. | Partial-refund test passes; expected amount is not assumed to equal order total. |
| 5 | Build HTTPS webhook endpoint, signature verification and event deduplication. | Build refund case timeline, discrepancy explanation and action-draft UX. | Verified event updates state; duplicate event does not double-count. |
| 6 | Harden state transitions, event logs and failure handling; support event/resource lookup if needed. | Implement AI tool functions grounded in records and uncertainty display. | AI explains seeded case using database facts; no fabricated status. |
| 7 | Build price-data adapter and scheduled threshold-check function with backend tests. | Implement price comparison/watchlist/history chart/target alert. | New price observation can trigger an alert; source/sample labels visible. |
| 8 | Integration testing, security checks, deployment configuration and persistence choice. | Polish UI, add budget summary and empty/error states; write draft README. | Fresh environment setup succeeds; hosted persistence strategy validated. |
| 9 | Fix integration defects; verify webhook delivery on deployed HTTPS endpoint. | Prepare screenshots/demo script, test price and AI scenarios, finalize tool disclosure. | All must-pass acceptance criteria pass; no secret in repository. |
| 10 | Run end-to-end tests, freeze code, verify deployed demo and repo. | Record public <3-minute video; final README/license and submission checklist. | Submission package complete; no new features after freeze. |

## 11.1 Daily working rhythm

Start of day: agree interface contracts, issues and test case for that day's output.

Midday: one person reviews the other's progress and resolves blockers early.

End of day: merge working code, run the end-to-end path, update README and note open risks.

Freeze scope after Day 7. Only fix defects and improve reliability during Days 8–10.

# 12. Suggested repository structure

pennypilot-ai/
├── app.py
├── requirements.txt
├── README.md
├── LICENSE
├── .gitignore
├── .env.example
├── src/
│   ├── config.py
│   ├── database/
│   │   ├── connection.py
│   │   ├── schema.sql
│   │   └── repositories.py
│   ├── paypal/
│   │   ├── client.py
│   │   ├── orders.py
│   │   ├── refunds.py
│   │   └── webhooks.py
│   ├── refunds/
│   │   ├── calculations.py
│   │   ├── matching.py
│   │   └── alerts.py
│   ├── ai/
│   │   ├── receipt_extraction.py
│   │   ├── assistant.py
│   │   └── recommendations.py
│   ├── pricing/
│   │   ├── data_provider.py
│   │   ├── history.py
│   │   ├── forecasting.py
│   │   └── alerts.py
│   └── ui/
│       ├── overview.py
│       ├── orders.py
│       ├── refunds.py
│       ├── prices.py
│       └── assistant.py
├── data/
│   └── sample_prices.csv
├── tests/
│   ├── test_refund_calculations.py
│   ├── test_partial_refunds.py
│   ├── test_paypal_events.py
│   └── test_price_alerts.py
└── docs/
    ├── architecture.md
    ├── api-flow.md
    └── demo-script.md

# 13. Testing plan and acceptance criteria

| ID | Scenario | Expected result / pass condition | Priority |
| --- | --- | --- | --- |
| AC-01 | Sandbox checkout and capture | Valid test order is approved/captured; app stores order ID, capture ID, amount, currency and returned status. | Must |
| AC-02 | ₹5,000 order with three items; two returned | Expected refund is computed from returned items and known adjustments, not original order total. | Must |
| AC-03 | Partial refund received | Confirmed amount is recorded; outstanding = max(0, expected − confirmed). | Must |
| AC-04 | Repeated webhook | Duplicate provider event is acknowledged safely and does not double-count. | Must |
| AC-05 | Invalid webhook signature | Event is rejected/not applied to verified financial state; safe log created. | Must |
| AC-06 | Unknown/unmatched refund | Record is flagged for review; system does not arbitrarily assign it to an item. | Must |
| AC-07 | AI extraction has missing/uncertain field | UI asks user to confirm/correct; uncertain field is not silently treated as verified. | Must |
| AC-08 | Price falls below target | New timestamped observation triggers one in-app alert; repeated check does not spam duplicate alerts. | Must |
| AC-09 | Insufficient price history | Assistant states insufficient data rather than inventing a forecast. | Must |
| AC-10 | Fresh setup from README | Another person can install dependencies, configure environment and run the demo using documented steps. | Must |
| AC-11 | Public repository hygiene | No secrets or personal receipts committed; LICENSE and .env.example present. | Must |
| AC-12 | Hosted demo | Core flow is usable from a fresh browser session; storage survives the demo's expected lifecycle. | Must |

## 13.1 Edge cases that must be tested

Multiple returned items; return of only part of a quantity; discounts or shipping adjustments.

Refund arrives in multiple parts; a refund is pending, failed, or later updated.

Webhook arrives twice or out of order; database temporarily unavailable.

User edits an AI-extracted amount; order total does not match sum of items.

Price data is stale, unavailable, in a different currency, or refers to a non-identical product.

Provider returns an order-level refund with no item mapping; leave item allocation unresolved until evidence exists.

# 14. Deployment and reliability

## 14.1 Local development

Clone the public repository and create a Python virtual environment.

Install requirements from requirements.txt.

Copy .env.example to .env and add sandbox credentials and the chosen AI configuration locally.

Initialize the database using the schema/migration instructions.

Run Streamlit and any separate FastAPI webhook service using the documented commands.

Use PayPal Sandbox and synthetic sample data only.

## 14.2 Hosted demo

Choose a host that supports Python and the required HTTPS endpoint. Confirm current free-tier limits before committing to it.

Store secrets in host environment settings; never in code, screenshots, logs or the public README.

Free Render web services can sleep after inactivity and have ephemeral local filesystems; a local SQLite database may be lost on restart/redeploy. Render's free Postgres has a stated 30-day expiry, so do not treat it as permanent storage. Verify current terms at deployment time.

If a reliable hosted webhook or persistent database cannot be provided at ₹0, keep the core demo reproducible locally and disclose the hosted limitation. Do not fake provider events and call them live.

Keep a seeded demo dataset and a reset script so judges can reproduce the same scenario.

## 14.3 Security and privacy

Use synthetic/sample receipts for public demo; do not upload real bank statements or sensitive personal records to public repositories.

Validate file type and size; do not execute uploaded files.

Restrict AI context to the current user's records; do not send unnecessary data to an LLM.

Verify PayPal webhook authenticity and use unique event IDs for idempotency.

Keep payment/refund state transitions in backend logic, not client-side UI or AI prompts.

Add clear labels for sandbox/test transactions, sample prices and user-entered evidence.

# 15. GitHub, README and license requirements

## 15.1 Repository checklist

Repository is public on GitHub (or another allowed public Git repository host).

An appropriate open-source LICENSE file is visible at the repository root; confirm compatibility with all dependencies and hackathon rules.

README includes project purpose, features, architecture, setup, environment variables, PayPal Sandbox instructions, AI tools and limitations, tests, deployment, demo URL and screenshots.

.env.example contains placeholder variable names only; .env is ignored by Git.

All required source code, sample assets and instructions are committed; no secrets or real personal/financial documents are committed.

requirements.txt pins or bounds dependencies enough for reproducible setup.

Document which data is live, sandbox, user-entered or sample.

## 15.2 README outline

Project name, one-sentence value proposition and demo link

Problem and target user

Feature list and screenshots

Architecture/data-flow diagram

Technology stack and AI tool usage

Prerequisites and local installation

Environment variable configuration

PayPal Sandbox setup and test journey

Sample dataset and known limitations

Run tests and troubleshoot common errors

Deployment instructions

License and credits

# 16. Three-minute demo video

| Time | What to show | Message |
| --- | --- | --- |
| 0:00–0:20 | Open the dashboard and state the problem. | Shopping is fragmented before and after purchase. |
| 0:20–0:55 | Show product comparison/history and set a target-price alert. | PennyPilot supports a better-informed purchase decision; identify live/sample data. |
| 0:55–1:35 | Run sandbox checkout/capture, then process a partial refund and show relevant IDs/status. | PayPal integration is real in Sandbox. |
| 1:35–2:15 | Show a ₹5,000 order, two returned items, ₹2,000 confirmed refund and ₹1,800 outstanding; ask AI to explain. | Item-level reconciliation and grounded AI solve the post-purchase problem. |
| 2:15–2:40 | Show webhook-driven status update and evidence timeline. | The product reacts to verified events and tracks resolution. |
| 2:40–3:00 | Show repository/demo link and summarize stack/impact. | The prototype is runnable, documented and reproducible. |

Record the working app on the device/platform it was built for.

Upload publicly to YouTube; include the URL in the hackathon submission.

Use only original or appropriately licensed visuals/audio; avoid copyrighted music and unpermitted third-party assets.

Prepare test accounts and seed data before recording. Do not spend video time on setup screens.

# 17. Risks and mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| PayPal Sandbox access or regional setup issue | Could block core integration. | Validate Day 1; consult current PayPal requirements; use official docs/Postman; do not leave API access until late. |
| No free reliable retailer price API | Live cross-store comparison may be unavailable. | Use a documented source if suitable; otherwise clearly label a small sample dataset and make the comparison/history workflow functional. |
| Webhook endpoint unreachable or host sleeps | No timely automatic status update. | Test deployed HTTPS early; keep a manual resource refresh/test path for debugging; disclose hosting constraints. |
| AI extracts wrong amounts | Incorrect refund expectation or user trust damage. | Validate schema/totals; require user review; never let AI directly set confirmed refund status. |
| Partial refund logic double-counts | Financial totals wrong. | Use provider refund IDs/event IDs, unique constraints and unit tests. |
| Scope too large for 10 days | Incomplete submission. | Freeze MVP scope by Day 1; price forecasting and live multi-retailer coverage are stretch goals. |
| Secrets or sensitive files exposed | Security/privacy failure. | Use environment variables, .gitignore, synthetic demo data and repository secret scanning. |
| Free hosting loses data | Demo state disappears. | Use a suitable persistent data option or local seeded demo; test restart/redeploy behavior. |
| AI costs exceed zero budget | Unexpected spend. | Local model first or enforce a small API usage cap; use short prompts and synthetic records. |

# 18. Definition of done

The project is ready to submit only when all must-pass acceptance criteria are checked, the demo can be reproduced, and the team can explain the boundaries of each integration.

☐ A PayPal Sandbox order is captured through the implemented API flow.

☐ A refund against an eligible captured test payment is recorded, with a verified status/event path.

☐ A partial-return example calculates the correct expected, confirmed and outstanding amounts.

☐ Webhook authenticity and duplicate-event handling are tested.

☐ AI receipt extraction works on a sample receipt and exposes fields for correction.

☐ AI explanation is based on stored records and does not invent payment confirmation.

☐ Price comparison/history and target-price alert work using an identified source or clearly labelled sample data.

☐ The application is interactive and persistent enough for the demo.

☐ Public repository, license, README, requirements and environment example are complete.

☐ Public YouTube video is under three minutes and linked in the submission.

# 19. Final decisions to make on Day 1

| Decision | Recommended default | Must be confirmed |
| --- | --- | --- |
| AI provider | Local model for ₹0-first; hosted API only if quality requires it. | Hardware capability, image support, current API price/credits. |
| Price source | One permitted API or labelled sample CSV. | Terms, target retailer coverage, historical data, quota and cost. |
| Deployment | Streamlit UI plus separate HTTPS webhook service if required. | Host supports endpoint, secrets, and expected uptime. |
| Database | SQLite for local demo; persistent managed DB if hosted state must survive restarts. | Free-tier retention, limits and reset plan. |
| MVP feature freeze | PayPal flow + item-level refund reconciliation + receipt AI + one price-watch workflow. | Both teammates agree no additional major features before core tests pass. |

# Appendix A — Key official documentation

These are the starting references used to define the integration plan. Re-check them during implementation because API requirements, prices, account eligibility and hosting terms can change.

PayPal REST APIs: https://developer.paypal.com/api/rest/

PayPal getting started / Sandbox accounts: https://developer.paypal.com/api/get-started/

PayPal REST webhook integration and verification: https://developer.paypal.com/api/rest/webhooks/rest/

PayPal webhooks overview: https://developer.paypal.com/api/webhooks/overview/

PayPal Payments API specification (refund/capture concepts): https://github.com/paypal/paypal-rest-api-specifications

Render free deployment limitations: https://render.com/docs/free

Render pricing: https://render.com/pricing

Streamlit documentation: https://docs.streamlit.io/

Ollama documentation: https://docs.ollama.com/

OpenAI API pricing: https://openai.com/api/pricing/

GitHub licensing guidance: https://docs.github.com/articles/licensing-a-repository

FINAL BUILD PRINCIPLE Build a small, verifiable end-to-end workflow first. Keep financial truth in deterministic code and verified provider events; use AI for extraction, matching assistance and explanations; clearly label data sources and limitations.